| Uva Wellassa University of Sri Lanka Faculty of Applied Sciences Department of Computer Science and Informatics Undergraduate Research Project (CST/IIT)- 2024/2025 |  |  |  |  |
| --- | --- | --- | --- | --- |
| PROGRESS REPORT Report No: |  |  |  |  |
| Name of the student/s: | W.K.Gayan |  |  |  |
| Registration Number/s: | UWU/IIT/21/062 |  |  |  |
| Degree Programme/s: | Industrial Information Technology |  |  |  |
| Title of the Study: | AI-Based Tomato Ripening Stage Detection and Sorting System with Shelf-Life Estimation for the Commonly Consumed Padma Variety in Sri Lanka Using Computer Vision and Conveyor Automation |  |  |  |
| Institute/s where studies are affiliated with: | Uva Wellassa University of Sri Lanka |  |  |  |
| Name of the Supervisor/s: | Ms. D.P. Jayathunga(Principle supervisor) Dr. U.G.A.T. Premathilake (Co-Supervisor) Ms. M.P.A.M. Rathnakumara (Co-Supervisor) |  |  |  |
| Period of Progress: | From:29/03/2026 |  | To:29/04/2026 |  |
| Progress (A description by the student). |  |  |  |  |
| ### 1) Accomplished activities During this period, the project transitioned from conceptual design to technical validation. The primary focus was on refining the 3D SolidWorks prototype to ensure mechanical feasibility before moving to the fabrication stage. By stress-testing the CAD model virtually, I identified critical alignment requirements for the motor mounts and sensor brackets. Simultaneously, the YOLOv8 multi-class detection model underwent hyperparameter tuning and evaluation against the initial dataset to ensure the ripeness classification for the "Padma" variety meets the required precision for real-time sorting. Milestones achieved - Finalized 3D Assembly Design: Completed the SolidWorks assembly, including refined tolerances for the conveyor frame and actuator housing. - Virtual Clearance Calibration: Conducted a clearance analysis within the CAD environment to ensure the camera’s Field of View (FoV) is unobstructed by lighting mounts. - Model Performance Review: Evaluated the YOLOv8 training logs (mAP and loss curves) to identify specific ripening stages that require augmented data. - Documentation Alignment: Synchronized the hardware bill of materials (BOM) with the updated 3D design to prevent procurement errors. ### 2) Activities planned for the Next Period The upcoming phase will shift from the virtual environment to component sourcing and initial hardware integration. The goal is to move from a "Build-Ready" design to a functional sub-assembly. Planned activities - Procurement & Sourcing: Finalize the selection of the conveyor motor and sensors based on the torque and sensitivity requirements confirmed in the CAD phase. - Camera & Lighting Synchronization: Perform physical testing of camera focal lengths using a mock-up stand to match the SolidWorks positioning. - Logic Development: Begin drafting the Python integration script that bridges the YOLOv8 detection output with the hardware trigger (Actuator control). - Dataset Expansion: Collect additional images of tomatoes in varied lighting conditions to improve the model's robustness. - Prototype Base Assembly: Begin the physical construction of the conveyor frame. |  |  |  |  |
| Signature of the Student: |  |  |  |  |
| Approval Signature of Supervisor: |  |  |  |  |
| Approval Signature of Co-Supervisor (If any): |  |  |  |  |
| Date: |  | 29/04/2026 |  |  |